## TicketLog3rdS
ID | Ticketart | Phase | Beschreibung | Use Case | Estimated Time (h) | Time spent (h) | Member | Member Time spent (h) | Team Member | Overall Time Spent (h) | Lecture Requirements (h) | Analysis & Design (h) | Implementation (h) | Testing (h)
DHTD-2 | Analysis & Design | Elaboration | Create structure of gameengine for Tower, Enemies and MatchField |  | 8 | 10 | Fabian | 10 | Fabian | 55.75 | 7.25 | 15.75 | 26 | 6.75
DHTD-3 | Implementation | Elaboration | Create Home activity | start the game from the menu | 4 | 4 | Nicolas | 4 | Luca | 44.75 | 13.25 | 21.25 | 6.75 | 3.5
DHTD-4 | Lecture Requirements | Inception | Blog Entry Week 2 |  | 2 | 1.91 | Nicolas | 1.75 | Nicolas | 74.91 | 30.66 | 15.75 | 19.75 | 8.75
[7 empty] | Nicolas | 0.16
DHTD-5 | Analysis & Design | Elaboration | create structure of gameengine for the Map |  | 8 | 3.75 | Luca | 3.75
DHTD-6 | Lecture Requirements | Inception | Write comments to other groups (Week 2) |  | 1 | 0.5 | Nicolas | 0.5
DHTD-8 | Lecture Requirements | Inception | Blog Entry Week 3 |  | 1.5 | 1.25 | Nicolas | 1.25
DHTD-9 | Lecture Requirements | Inception | Write comments to other groups (Week 3) |  | 1 | 1 | Luca | 1 | Type | Overall Time (h)
DHTD-10 | Analysis & Design | Inception | Create UCD and SRS |  | 6 | 6 | Fabian | 2 | Lecture Requirements | 51.16
[7 empty] | Nicolas | 4 | Analysis & Design | 52.75
DHTD-11 | Analysis & Design | Inception | Create Use-Case-Specifications for two Use-Cases | start the game from the menu | 8 | 7 | Luca | 1 | Implementation | 52.5
[7 empty] | Fabian | 1 | Testing | 19
[7 empty] | Nicolas | 1.5
|  |  |  | start waves |  |  | Luca | 1
[7 empty] | Fabian | 1 | Use Case | Overall Time (h)
[7 empty] | Nicolas | 1.5 | start the game from the menu | 43
DHTD-12 | Lecture Requirements | Inception | Blog Entry Week 4 |  | 1.5 | 1 | Nicolas | 1 | start waves | 7
DHTD-13 | Lecture Requirements | Inception | Write comments to other groups (Week 4) |  | 1 | 1 | Luca | 1 | build towers on selected area | 6.5
DHTD-14 | Lecture Requirements | Inception | Blog Entry Week 5 |  | 2 | 1.5 | Nicolas | 1.5 | return to main menu | 1.5
DHTD-15 | Analysis & Design | Inception | Write Narratives for two use cases | start the game from the menu | 2 | 3 | Nicolas | 0.5
[7 empty] | Luca | 0.5
[7 empty] | Fabian | 0.5
|  |  |  | start waves |  |  | Nicolas | 0.5
[7 empty] | Luca | 0.5
[7 empty] | Fabian | 0.5
DHTD-16 | Lecture Requirements | Inception | write comments to other groups (Week 5) |  | 1 | 1 | Nicolas | 0.5
[7 empty] | Luca | 0.5
DHTD-17 | Testing | Elaboration | Write unit tests for gameengine |  | 4 | 4.25 | Fabian | 4
[7 empty] | Luca | 0.25
DHTD-18 | Lecture Requirements | Inception | Write comments to other groups (Week 6) |  | 1 | 1 | Luca | 1
DHTD-19 | Lecture Requirements | Inception | Blog Entry Week 6 |  | 1.5 | 2.25 | Fabian | 1.5
[7 empty] | Nicolas | 0.75
DHTD-20 | Lecture Requirements | Elaboration | Refactor project management tool in order to match requirements |  | 8 | 6 | Nicolas | 6
DHTD-21 | Implementation | Elaboration | Hello World Demo: Visualization of simple gameengine elements | start the game from the menu | 8 | 6 | Fabian | 6
DHTD-22 | Lecture Requirements | Elaboration | Blog Entry Week 7 |  | 1.5 | 1.5 | Nicolas | 1
[7 empty] | Fabian | 0.5
DHTD-23 | Implementation | Construction | Gameengine improve class "Bullet" -> create tower shooting animation |  | 16 | 15.5 | Nicolas | 11.5
[7 empty] | Fabian | 4
DHTD-25 | Implementation | Construction | Visualize the map of the gameengine and add listener | start the game from the menu | 12 | 17 | Fabian | 11
[7 empty] | Nicolas | 3
[7 empty] | Luca | 3
DHTD-28 | Lecture Requirements | Elaboration | Write comments to other groups (Week 7) |  | 2 | 1 | Luca | 1
DHTD-29 | Analysis & Design | Elaboration | design a simple tank drawable |  | 4 | 4 | Nicolas | 4
DHTD-30 | Analysis & Design | Elaboration | design a simple tower drawable |  | 4 | 3.5 | Luca | 3.5
DHTD-31 | Lecture Requirements | Elaboration | Blog Entry Week 8 |  | 1 | 2 | Nicolas | 2
DHTD-32 | Lecture Requirements | Elaboration | Write comments to other groups (Week 8) |  | 1 | 1 | Nicolas | 1
DHTD-35 | Implementation | Construction | Calculate the exact angle and align the tower to enemies |  | 4 | 3.5 | Luca | 3
[7 empty] | Nicolas | 0.5
DHTD-36 | Analysis & Design | Elaboration | Create the background-map for the game-page |  | 2 | 2 | Luca | 2
DHTD-39 | Analysis & Design | Construction | Create Path-Designs and implement into the game |  | 8 | 8 | Luca | 8
DHTD-40 | Testing | Elaboration | Feature Files and automatic testing with Cucumber | start the game from the menu | 8 | 11 | Fabian | 2.5
[7 empty] | Nicolas | 8.5
DHTD-41 | Testing | Construction | Unit Test for tower rotation |  | 5 | 3.75 | Luca | 3.25
[7 empty] | Fabian | 0.25
[7 empty] | Nicolas | 0.25
DHTD-42 | Lecture Requirements | Elaboration | Blog Entry Week 9 |  | 3 | 4 | Fabian | 1
[7 empty] | Luca | 2
[7 empty] | Nicolas | 1
DHTD-43 | Lecture Requirements | Elaboration | Write comments to other groups (Week 9) |  | 1 | 1 | Luca | 1
DHTD-44 | Analysis & Design | Elaboration | Create MVC model |  | 3 | 2 | Fabian | 0.75
[7 empty] | Luca | 0.5
[7 empty] | Nicolas | 0.75
DHTD-38 | Implementation | Construction | GE: Build towers when a button is clicked | build towers on selected area | 2 | 2.5 | Fabian | 2
[7 empty] | Nicolas | 0.25
[7 empty] | Luca | 0.25
DHTD-49 | Implementation | Construction | GE: remove Tower on click | build towers on selected area | 2 | 2 | Fabian | 1.5
[7 empty] | Nicolas | 0.25
[7 empty] | Luca | 0.25
DHTD-50 | Implementation | Construction | GE: spawn wave button | start waves | 2 | 2 | Fabian | 1.5
[7 empty] | Nicolas | 0.25
[7 empty] | Luca | 0.25
DHTD-46 | Analysis & Design | Inception | Create UCS for UC "build towers on selected area" | build towers on selected area | 3 | 2 | Nicolas | 1.75
[7 empty] | Luca | 0.25
DHTD-47 | Analysis & Design | Inception | Create UCS for UC "Return to main menu" | return to main menu | 2 | 1.5 | Nicolas | 1.25
[7 empty] | Luca | 0.25
DHTD-54 | Lecture Requirements | Elaboration | create handout for midterm presentation |  | 4 | 3.5 | Nicolas | 3.25
[7 empty] | Luca | 0.25
DHTD-53 | Lecture Requirements | Elaboration | create the presentation for midterm exam |  | 15 | 12.25 | Nicolas | 5.5
[7 empty] | Luca | 4.5
[7 empty] | Fabian | 4.25
DHTD-51 | Lecture Requirements | Elaboration | Blog Entry Week 10 |  | 6 | 3.5 | Nicolas | 3.5
DHTD-52 | Lecture Requirements | Elaboration | Write Comments to other groups (Week 10) |  | 1 | 1 | Luca | 1

## TicketLog4thS
ID | Ticketart | Phase | Beschreibung | Use Case | Estimated Time (h) | Time spent (h) | Member | Member Time spent (h) | Team Member | Overall Time Spent (h) | Project Management (h) | Analysis & Design (h) | Implementation (h) | Testing (h)
DHTD-55 | Analysis & Design | Elaboration | Create UCS for UC "Upgrade Towers" | upgrade towers | 2 | 3.75 | Fabian | 0.5 | Fabian | 100.75 | 12 | 4.5 | 83 | 1.25
[7 empty] | Luca | 2.5 | Luca | 61.5 | 13 | 6 | 40.5 | 2
[7 empty] | Nicolas | 0.75 | Nicolas | 119.25 | 37.25 | 27 | 37 | 18
DHTD-56 | Analysis & Design | Elaboration | Create UCS for UC "Sell Towers" | sell towers | 2 | 2.75 | Fabian | 0.5
[7 empty] | Luca | 1.5
[7 empty] | Nicolas | 0.75
DHTD-57 | Analysis & Design | Elaboration | Create UCS for UC "Select between different Towers" | select beween different towers | 2 | 2 | Fabian | 2
DHTD-58 | Analysis & Design | Elaboration | Create UCS for UC "Edit Settings" | edit settings | 2 | 1 | Nicolas | 1 | Type | Overall Time (h)
DHTD-59 | Analysis & Design | Elaboration | Create UCS for UC "Toggle Sound & Animations" | toggle sound & animations | 2 | 1.5 | Fabian | 0.5 | Lecture Requirements | 62.25
[7 empty] | Luca | 0.5 | Analysis & Design | 37.5
[7 empty] | Nicolas | 0.5 | Implementation | 160.5
DHTD-60 | Analysis & Design | Elaboration | Create UCS for UC "Play multiple Levels with different Difficulties" | choose difficulties | 2 | 2.25 | Fabian | 0.75 | Testing | 21.25
[7 empty] | Luca | 0.75
[7 empty] | Nicolas | 0.75
DHTD-61 | Project Management | Elaboration | Refactor Blog-Links |  | 0.25 | 0.25 | Nicolas | 0.25 | Use Case | Overall Time (h)
DHTD-62 | Project Management | Elaboration | Refactor Activity Diagrams of first 4 Use Cases |  | 2 | 1 | Luca | 0.75 | upgrade towers | 12.375
[7 empty] | Nicolas | 0.25 | sell towers | 10.125
DHTD-63 | Project Management | Elaboration | Check for the film of the .feature-file tests |  | 0.25 | 0.25 | Nicolas | 0.25 | select between different towers | 26
DHTD-64 | Project Management | Elaboration | Generate Jira-Gantt-Chart and Pie-Chart (Workflow) [and Cumulative Chart] |  | 1 | 0.75 | Nicolas | 0.75 | edit settings | 12.5
DHTD-65 | Project Management | Elaboration | Refactor Jira-Sprint-Names (week X + one-word-description) |  | 1 | 0.5 | Nicolas | 0.5 | toggle sound & animations | 1.5
DHTD-66 | Project Management | Elaboration | Blog Entry Week 11 |  | 2 | 1.75 | Nicolas | 1.75 | choose difficulties | 15.5
DHTD-67 | Project Management | Elaboration | Create Risk-Management Table and publish |  | 1.5 | 2.25 | Fabian | 0.75
[7 empty] | Luca | 0.75
[7 empty] | Nicolas | 0.75
DHTD-68 | Project Management | Elaboration | Create UC-Overview-Table |  | 2 | 0.75 | Fabian | 0.25
[7 empty] | Nicolas | 0.5
DHTD-69 | Project Management | Elaboration | Blog Entry Week 12 |  | 1.5 | 2 | Fabian | 1.25
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 0.5
DHTD-70 | Project Management | Elaboration | Write comments to other groups (Week 12) |  | 1 | 0.75 | Luca | 0.75
DHTD-71 | Implementation | Construction | Introduce soundtrack-theme on main page |  | 2 | 2.5 | Fabian | 2.5
DHTD-26 | Implementation | Elaboration | GE: imlement money |  | 8 | 8 | Fabian | 8
DHTD-27 | Implementation | Elaboration | GE: implement life points for the game |  | 4 | 2 | Fabian | 2
DHTD-72 | Implementation | Construction | Implement the menu for choosing different towers | select between different towers | 16 | 24 | Fabian | 7.5
[7 empty] | Luca | 13.5
[7 empty] | Nicolas | 3
DHTD-73 | Implementation | Construction | Implement UC "Choose Difficulties" | choose difficulties | 10 | 13.25 | Fabian | 1
[7 empty] | Luca | 1
[7 empty] | Nicolas | 11.25
DHTD-74 | Project Management | Construction | Write comments to other groups (Week 13) |  | 1 | 1 | Nicolas | 1
DHTD-75 | Project Management | Elaboration | Blog Entry Week 13 |  | 2.5 | 2 | Fabian | 1
[7 empty] | Nicolas | 1
DHTD-76 | Project Management | Elaboration | Refactoring of Risk Management and UC Table |  | 1 | 1 | Nicolas | 1
DHTD-77 | Project Management | Elaboration | Function Points Calculation |  | 4 | 6 | Fabian | 1.5
[7 empty] | Luca | 1.5
[7 empty] | Nicolas | 3
DHTD-24 | Testing | Construction | Gameengine improve unit tests |  | 6 | 1.5 | Nicolas | 1.5
DHTD-37 | Implementation | Construction | GE improve Bullet mechanism -> avoid game crash and adjust calculations |  | 5 | 5.25 | Fabian | 0.25
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 4.75
DHTD-78 | Implementation | Construction | Implement UC Edit Settings | edit settings | 8 | 11.5 | Fabian | 11
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 0.25
DHTD-79 | Implementation | Construction | Implement UC upgrade and sell Tower | sell towers | 12 | 14.75 | Fabian | 0.5
[7 empty] | Luca | 13.75
[7 empty] | Nicolas | 0.5
DHTD-80 | Implementation | Construction | Implement a new tower called freezer |  | 8 | 2.25 | Fabian | 1.75
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 0.25
DHTD-81 | Implementation | Construction | Implement new tower boombastic |  | 8 | 4.5 | Fabian | 4
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 0.25
DHTD-86 | Project Management | Construction | Blog Entry Week 14 |  | 3 | 2 | Luca | 0.5
[7 empty] | Nicolas | 1.5
DHTD-87 | Project Management | Construction | Write comments to other groups (Week 14) |  | 0.5 | 0.75 | Nicolas | 0.75
DHTD-92 | Implementation | Construction | Implement explosion animation if enemy dies |  | 2 | 2 | Fabian | 2
DHTD-93 | Analysis & Design | Construction | Create new design for tower freezer |  | 3 | 1.75 | Nicolas | 1.75
DHTD-94 | Testing | Construction | Setup Test Environment |  | 8 | 4.5 | Nicolas | 4.5
DHTD-95 | Analysis & Design | Construction | Create new design for tower boombastic |  | 3 | 3.5 | Nicolas | 3.5
DHTD-45 | Analysis & Design | Construction | create bullet-design and implement into the game |  | 1 | 0.75 | Nicolas | 0.75
DHTD-82 | Implementation | Construction | Implement new plasmatower |  | 5 | 8 | Fabian | 4.25
[7 empty] | Nicolas | 3.75
DHTD-96 | Project Management | Construction | Blog Entry Week 15 |  | 2 | 1.5 | Fabian | 0.5
[7 empty] | Luca | 0.5
[7 empty] | Nicolas | 0.5
DHTD-97 | Project Management | Construction | Write comments to other groups (Week 15) |  | 1 | 1 | Fabian | 1
DHTD-98 | Project Management | Construction | Refactoring of given project |  | 6 | 6.5 | Fabian | 1.5
[7 empty] | Luca | 2
[7 empty] | Nicolas | 3
DHTD-99 | Analysis & Design | Construction | Create design for tower plasmarizer |  | 3 | 3.5 | Nicolas | 3.5
DHTD-100 | Analysis & Design | Construction | Create design for tower assault laser |  | 3 | 3 | Nicolas | 3
DHTD-83 | Implementation | Construction | Implement new laser tower |  | 12 | 14 | Fabian | 6
[7 empty] | Luca | 3.5
[7 empty] | Nicolas | 4.5
DHTD-101 | Project Management | Construction | Blog Entry Week 16 |  | 2.5 | 2 | Fabian | 0.75
[7 empty] | Luca | 0.5
[7 empty] | Nicolas | 0.75
DHTD-102 | Project Management | Construction | Write comments to other groups (Week 16) |  | 1 | 1 | Luca | 1
DHTD-103 | Analysis & Design | Construction | Create designs/icons for settings menu |  | 1.5 | 2 | Luca | 0.25
[7 empty] | Nicolas | 1.75
DHTD-105 | Analysis & Design | Construction | Add design pattern to project |  | 8 | 3 | Fabian | 0.25
[7 empty] | Nicolas | 2.75
DHTD-104 | Analysis & Design | Construction | Create design for car enemy |  | 3 | 3.5 | Nicolas | 3.5
DHTD-107 | Project Management | Transition | Update Time Sheet (Sprint 11-16) |  | 1 | 1.25 | Nicolas | 1.25
DHTD-108 | Project Management | Construction | Blog Entry Week 17 |  | 2.5 | 3 | Fabian | 0.5
[7 empty] | Luca | 0.5
[7 empty] | Nicolas | 2
DHTD-109 | Project Management | Construction | Write comments to other groups (Week 17) |  | 1 | 1 | Luca | 1
DHTD-110 | Implementation | Construction | Create levels for towers | upgrade towers | 2 | 1.25 | Luca | 1.25
DHTD-111 | Implementation | Construction | Lasertower: Check if it is posssible to make multiple damage |  | 3 | 1.5 | Fabian | 1
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 0.25
DHTD-112 | Testing | Construction | Refactor code snippets according to Metrics |  | 6 | 5.25 | Nicolas | 5.25
DHTD-113 | Testing | Construction | Improve Test Automation |  | 8 | 6.25 | Fabian | 0.5
[7 empty] | Luca | 0.5
[7 empty] | Nicolas | 5.25
DHTD-84 | Implementation | Construction | Implement new enemy car |  | 4 | 2 | Luca | 0.75
[7 empty] | Nicolas | 1.25
DHTD-85 | Implementation | Construction | implement new enemy plane |  | 3 | 2.75 | Fabian | 2.25
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 0.25
DHTD-88 | Implementation | Construction | Design the easy match |  | 4 | 2.75 | Fabian | 0.25
[7 empty] | Luca | 2.25
[7 empty] | Nicolas | 0.25
DHTD-91 | Implementation | Construction | Implement boss enemy |  | 4 | 3.75 | Fabian | 3.25
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 0.25
DHTD-106 | Implementation | Construction | Bug: Tower Radius is below newly spawned enemies |  | 3 | 0.25 | Nicolas | 0.25
DHTD-114 | Implementation | Construction | Ingame Music |  | 14 | 14 | Fabian | 14
DHTD-115 | Implementation | Transition | Bugfixes |  | 4 | 3 | Fabian | 2
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 0.75
DHTD-116 | Project Management | Construction | Blog Entry Week 18 |  | 1 | 1.5 | Fabian | 0.25
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 1
DHTD-117 | Testing | Transition | Create question formular for UX test |  | 3 | 2.25 | Fabian | 0.25
[7 empty] | Luca | 1
[7 empty] | Nicolas | 1
DHTD-118 | Analysis & Design | Elaboration | Create design for plane enemy |  | 3 | 2.75 | Nicolas | 2.75
DHTD-89 | Implementation | Construction | Design the medium match |  | 2 | 1.5 | Luca | 1.5
DHTD-90 | Implementation | Construction | Design the hard match |  | 3 | 1 | Luca | 1
DHTD-119 | Implementation | Construction | Implement enemy life bar |  | 4 | 4 | Fabian | 4
DHTD-120 | Implementation | Construction | Bugfixes |  | 6 | 10.75 | Fabian | 5.5
[7 empty] | Nicolas | 5.25
DHTD-121 | Analysis & Design | Transition | Balancing |  | 4 | 0.5 | Luca | 0.5
DHTD-122 | Project Management | Transition | Blog Entry Week 19 |  | 2.5 | 1.75 | Fabian | 0.25
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 1.25
DHTD-124 | Project Management | Transition | Blog Entry Week 20 |  | 1.5 | 2 | Fabian | 0.25
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 1.5
DHTD-125 | Testing | Transition | Carry out Usability Test |  | 2 | 1.5 | Fabian | 0.5
[7 empty] | Luca | 0.5
[7 empty] | Nicolas | 0.5
DHTD-126 | Project Management | Transition | Blog Entry Week 21 |  | 2 | 2 | Nicolas | 2
DHTD-127 | Project Management | Transition | Burndown Diagram Screenshots on Website |  | 1 | 1 | Nicolas | 1
DHTD-128 | Project Management | Transition | Create Video of TowerDefense App |  | 2 | 2 | Fabian | 0.25
[7 empty] | Luca | 0.25
[7 empty] | Nicolas | 1.5
DHTD-129 | Project Management | Transition | Update Presentation for Final |  | 8 | 8.75 | Fabian | 2
[7 empty] | Luca | 2
[7 empty] | Nicolas | 4.75
DHTD-130 | Project Management | Transition | Make PDF out of the blog and complete the final handin |  | 3 | 3 | Nicolas | 3

## Charts Overall
Overall Data
Team Member | Overall Time Spent (h) | Project Management (h) | Analysis & Design (h) | Implementation (h) | Testing (h)
Fabian | 156.5 | 19.25 | 20.25 | 109 | 8
Luca | 106.25 | 26.25 | 27.25 | 47.25 | 5.5
Nicolas | 194.16 | 67.91 | 42.75 | 56.75 | 26.75
Type | Overall Time (h)
Project Management | 113.41
Analysis & Design | 90.25
Implementation | 213
Testing | 40.25

## Use Case Overview
UC | UC description | Documentation (h) | Coding (h) | Testing (h) | Warm-Up time (h) | Total (h) | FP | Estimation (h)
0 | GameEngine - Foundation | 0 | 42 | 9 | 0 | 51 | --- | ---
1 | start the game from the menu | 5 | 4 | 3 | 5 | 12 | 82 | ---
2 | start waves | 5 | 2 | 0.5 | 0 | 7.5 | 81 | ---
3 | build towers on selected area | 2 | 4.5 | 0 | 0 | 6.5 | 64 | ---
4 | return to main menu | 1.5 | 0 | 0 | 0 | 1.5 | 44 | ---
5 | Upgrade Towers | n/a | n/a | n/a | 0 | 12.375 | 80 | 10.1
6 | Sell Towers | n/a | n/a | n/a | 0 | 10.125 | 80 | 10.1
7 | Select between different Towers | n/a | n/a | n/a | 0 | 26 | 79 | 9.86
8 | Edit Settings | n/a | n/a | n/a | 0 | 12.5 | 58 | 4.3
9 | Toggle Sound & Animations | n/a | n/a | n/a | 0 | 1.5 | 66 | 6.4
10 | Choose Difficulties | n/a | n/a | n/a | 0 | 15.5 | 76 | 9.1

## FP Calculation
UC1: Start the game from the menu | RET | DET | FTR | Complexity | Amount | RETs | DETs | FTRs | FP-Calculator: | http://groups.umd.umich.edu/cis/course.des/cis525/js/f00/harvey/FP_Calc.html?tCountVal=0#FPCalc
External Inputs | --- | 2 | 1 | low | 3 |  | Play-Button, MainActivity | MainActivity | Complexity: | low | average | high
External Outputs | --- | 3 | 3 | low | 6 |  | Field-Buttons, Moving Tanks, generated Map | GameActivity, MapStructure, Game
External Queries | --- | 0 | 0 | low | 0 |  | --- | --- | RET: Record Element Type
Internal Logical Files | 2 | 5 | --- | low | 7 | Tanks, Map | Tanks, Map, Fields, MatchField, Game |  | DET: Data Element Type
External Interface Files | 0 | 0 | --- | low | 0 | --- | --- |  | FTR: File Type Reference
Function Points | 82
UC2: Start Waves | RET | DET | FTR | Complexity | Amount | RETs | DETs | FTRs
External Inputs | --- | 1 | 2 | low | 3 |  | wave-button | GameActivity, Game, MatchField
External Outputs | --- | 2 | 2 | low | 4 |  | wave-button, Tanks | GameActivity, Game, MatchField
External Queries | --- | 0 | 0 | low | 0 |  | --- | ---
Internal Logical Files | 3 | 5 | --- | low | 8 | Game, MatchField, Enemies | Game, MatchField, Enemies, Tanks, MapStructure
External Interface Files | 0 | 0 | --- | low | 0 | --- | ---
Function Points | 81
UC3: Build Towers on selected Area | RET | DET | FTR | Complexity | Amount | RETs | DETs | FTRs
External Inputs | --- | 2 | 3 | average | 5 |  | Field-Buttons, Plus-Symbol | MatchField, Tower, Plus-Symbol
External Outputs | --- | 2 | 2 | low | 4 |  | Tower, MatchField | MatchField, Tower
External Queries | --- | 0 | 0 | low | 0 |  | --- | ---
Internal Logical Files | 2 | 2 | --- | low | 4 | Game, MatchField | Game, MatchField
External Interface Files | 0 | 0 | --- | low | 0 | --- | ---
Function Points | 64
UC4: Return to main menu | RET | DET | FTR | Complexity | Amount | RETs | DETs | FTRs
External Inputs | --- | 2 | 2 | low | 4 |  | Main-Menu-Button, GameActivity | GameActivity, Game
External Outputs | --- | 1 | 0 | low | 1 |  | MainActivity | ---
External Queries | --- | 0 | 0 | low | 0 |  | --- | ---
Internal Logical Files | 2 | 2 | --- | low | 4 | GameActivity, Game | GameActivity, Game
External Interface Files | 0 | 0 | --- | low | 0 | --- | ---
Function Points | 44
UC5: Upgrade Towers | RET | DET | FTR | Complexity | Amount | RETs | DETs | FTRs
External Inputs | --- | 2 | 2 | low | 4 |  | Tower-Selection, Upgrade-Button | Tower, GameActivity
External Outputs | --- | 3 | 2 | low | 5 |  | Tower, MatchField, GameActivity | Tower, GameActivity
External Queries | --- | 1 | 1 | low | 2 |  | Tower-Stats | Tower
Internal Logical Files | 3 | 3 | --- | low | 6 | GameActivity, Tower, Level-Constants | GameActivity, Tower, Upgrade-UI
External Interface Files | 0 | 0 | --- | low | 0 | --- | ---
Function Points | 80
Estimation: 10,1h
UC6: Sell Towers | RET | DET | FTR | Complexity | Amount | RETs | DETs | FTRs
External Inputs | --- | 2 | 2 | low | 4 |  | Tower-Selection, Sell-Button | Tower, GameActivity
External Outputs | --- | 3 | 2 | low | 5 |  | Tower, MatchField, GameActivity | Tower, GameActivity
External Queries | --- | 1 | 1 | low | 2 |  | Tower-Stats | Tower
Internal Logical Files | 3 | 3 | --- | low | 6 | GameActivity, Tower, MatchField | GameActivity, Tower, Sell-UI
External Interface Files | 0 | 0 | --- | low | 0 | --- | ---
Function Points | 80
Estimation: 10,1h
UC7: Select between different Towers | RET | DET | FTR | Complexity | Amount | RETs | DETs | FTRs
External Inputs | --- | 2 | 2 | low | 4 |  | Tower, Position | Tower, Game
External Outputs | --- | 2 | 2 | low | 4 |  | Tower-Selection, Select-Button | Tower, GameActivity
External Queries | --- | 2 | 1 | low | 3 |  | Money, Price | Game
Internal Logical Files | 3 | 3 | --- | low | 6 | GameActivity, Game, Tower-Template | GameActivity, Game, Money
External Interface Files | 0 | 0 | --- | low | 0 | --- | ---
Function Points | 79
Estimation: 9,86h
UC8: Edit Settings | RET | DET | FTR | Complexity | Amount | RETs | DETs | FTRs
External Inputs | --- | 1 | 2 | low | 3 |  | Menu-Button | GameActivity, Game
External Outputs | --- | 1 | 1 | low | 2 |  | Settings-UI | GameActivity
External Queries | --- | 1 | 1 | low | 2 |  | Settings | SharedPreferences
Internal Logical Files | 3 | 2 | --- | low | 5 | SharedPreferences, GameActivity, Game | Settings, GameActivity
External Interface Files | 0 | 0 | --- | low | 0 | --- | ---
Function Points | 58
Estimation: 4,3h
UC9: Toggle Sound & Animations | RET | DET | FTR | Complexity | Amount | RETs | DETs | FTRs
External Inputs | --- | 1 | 1 | low | 2 |  | Settings-Buttons | GameActivity
External Outputs | --- | 2 | 1 | low | 3 |  | Settings-Buttons, changed Settings | GameActivity
External Queries | --- | 1 | 1 | low | 2 |  | Settings | SharedPreferences
Internal Logical Files | 3 | 3 | --- | low | 6 | SharedPreferences, GameActivity, MainActivity | Settings, GameActivity, MainActivity
External Interface Files | 0 | 0 | --- | low | 0 | --- | ---
Function Points | 66
Estimation: 6,4h
UC10: Choose Difficulties | RET | DET | FTR | Complexity | Amount | RETs | DETs | FTRs
External Inputs | --- | 3 | 1 | low | 4 |  | MainActivity, Difficulty, Play-Button | MainActivity
External Outputs | --- | 3 | 1 | low | 4 |  | GameActivity, Game, Game-Settings | GameActivity
External Queries | --- | 1 | 1 | low | 2 |  | Statistics | SharedPreferences
Internal Logical Files | 3 | 3 | --- | low | 6 | SharedPreferences, MainActivity, GameActivity | Statistics, GameActivity, MainActivity
External Interface Files | 0 | 0 | --- | low | 0 | --- | ---
Function Points | 76
Estimation: 9,1h