## Tabelle1
ID | Risk Name | Risk Description | Risk Probability of Occurrence (1-3) | Risk Impact (1-3) | Risk Factor | Risk Mitigation | Person in Charge of Tracking | Number-Definitions:
1 | Publish problems | Unability to publish the app on Google Play | 1 | 3 | 3 | Publishing the app on our own server | Fabian | 1 = low | 2 = medium | 3 = high
2 | Lose team member | Losing a team member (e.g. due to failing exams) | 1 | 3 | 3 | Relieve group member if such a scenario becomes plausible; distribution of knowledge between all members | Luca
3 | Lack of time | Because of a huge workload in other lectures, team members might not have enough time to develop the use cases as planned | 2 | 2 | 4 | good and foresighted time management; setting priorities in order to achieve important goals | Luca
4 | Performance problems | As we do not have a lot of experience in developing Android games, there might be performance issues with our implementation | 2 | 3 | 6 | provide the possibility to turn off unnecessary animations and testing on several devices | Fabian
5 | Data loss (GitHub) | Technical problems or wrong usage can lead to data loss on GitHub | 1 | 3 | 3 | backup on multiple devices/servers and responsible usage of Git-tools | Nicolas
6 | Server loss | Jira and the blog are hosted on an own server | 1 | 2 | 2 | Regular backups | Nicolas
7 | Illness | Due to illness some team members could not be able to work anymore | 2 | 1 | 2 | distribution of knowledge between all members to reduce the impact | Luca
8 | Updates of tools | Because of software updates some used functionalities could not be useable anymore | 1 | 2 | 2 | no use of deprecated functionalities and updating only if necessary | Nicolas