## TicketLog3rdS
ID | Ticketart | Phase | Beschreibung | Use Case | Estimated Time (h) | Time spent (h) | Member | Member Time spent (h) | Team Member | Overall Time Spent (h) | Lecture Requirements (h) | Analysis & Design (h) | Implementation (h) | Testing (h)
DHTD-2 | Analysis & Design | Elaboration | Create structure of gameengine for Tower, Enemies and MatchField |  | 8 | 10 | Fabian | 10 | Fabian | 55.75 | 7.25 | 15.75 | 26 | 6.75
DHTD-3 | Implementation | Elaboration | Create Home activity | start the game from the menu | 4 | 4 | Nicolas | 4 | Luca | 44.75 | 13.25 | 21.25 | 6.75 | 3.5
DHTD-4 | Lecture Requirements | Inception | Blog Entry Week 2 |  | 2 | 1.91 | Nicolas | 1.75 | Nicolas | 74.91 | 30.66 | 15.75 | 19.75 | 8.75
[7 empty] | Nicolas | 0.16
DHTD-5 | Analysis & Design | Elaboration | create structure of gameengine for the Map |  | 8 | 3.75 | Luca | 3.75
DHTD-6 | Lecture Requirements | Inception | Write comments to other groups (Week 2) |  | 1 | 0.5 | Nicolas | 0.5
DHTD-8 | Lecture Requirements | Inception | Blog Entry Week 3 |  | 1.5 | 1.25 | Nicolas | 1.25
DHTD-9 | Lecture Requirements | Inception | Write comments to other groups (Week 3) |  | 1 | 1 | Luca | 1 | Type | Overall Time (h)
DHTD-10 | Analysis & Design | Inception | Create UCD and SRS |  | 6 | 6 | Fabian | 2 | Lecture Requirements | 51.16
[7 empty] | Nicolas | 4 | Analysis & Design | 52.75
DHTD-11 | Analysis & Design | Inception | Create Use-Case-Specifications for two Use-Cases | start the game from the menu | 8 | 7 | Luca | 1 | Implementation | 52.5
[7 empty] | Fabian | 1 | Testing | 19
[7 empty] | Nicolas | 1.5
|  |  |  | start waves |  |  | Luca | 1
[7 empty] | Fabian | 1 | Use Case | Overall Time (h)
[7 empty] | Nicolas | 1.5 | start the game from the menu | 43
DHTD-12 | Lecture Requirements | Inception | Blog Entry Week 4 |  | 1.5 | 1 | Nicolas | 1 | start waves | 7
DHTD-13 | Lecture Requirements | Inception | Write comments to other groups (Week 4) |  | 1 | 1 | Luca | 1 | build towers on selected area | 6.5
DHTD-14 | Lecture Requirements | Inception | Blog Entry Week 5 |  | 2 | 1.5 | Nicolas | 1.5 | return to main menu | 1.5
DHTD-15 | Analysis & Design | Inception | Write Narratives for two use cases | start the game from the menu | 2 | 3 | Nicolas | 0.5
[7 empty] | Luca | 0.5
[7 empty] | Fabian | 0.5
|  |  |  | start waves |  |  | Nicolas | 0.5
[7 empty] | Luca | 0.5
[7 empty] | Fabian | 0.5
DHTD-16 | Lecture Requirements | Inception | write comments to other groups (Week 5) |  | 1 | 1 | Nicolas | 0.5
[7 empty] | Luca | 0.5
DHTD-17 | Testing | Elaboration | Write unit tests for gameengine |  | 4 | 4.25 | Fabian | 4
[7 empty] | Luca | 0.25
DHTD-18 | Lecture Requirements | Inception | Write comments to other groups (Week 6) |  | 1 | 1 | Luca | 1
DHTD-19 | Lecture Requirements | Inception | Blog Entry Week 6 |  | 1.5 | 2.25 | Fabian | 1.5
[7 empty] | Nicolas | 0.75
DHTD-20 | Lecture Requirements | Elaboration | Refactor project management tool in order to match requirements |  | 8 | 6 | Nicolas | 6
DHTD-21 | Implementation | Elaboration | Hello World Demo: Visualization of simple gameengine elements | start the game from the menu | 8 | 6 | Fabian | 6
DHTD-22 | Lecture Requirements | Elaboration | Blog Entry Week 7 |  | 1.5 | 1.5 | Nicolas | 1
[7 empty] | Fabian | 0.5
DHTD-23 | Implementation | Construction | Gameengine improve class "Bullet" -> create tower shooting animation |  | 16 | 15.5 | Nicolas | 11.5
[7 empty] | Fabian | 4
DHTD-25 | Implementation | Construction | Visualize the map of the gameengine and add listener | start the game from the menu | 12 | 17 | Fabian | 11
[7 empty] | Nicolas | 3
[7 empty] | Luca | 3
DHTD-28 | Lecture Requirements | Elaboration | Write comments to other groups (Week 7) |  | 2 | 1 | Luca | 1
DHTD-29 | Analysis & Design | Elaboration | design a simple tank drawable |  | 4 | 4 | Nicolas | 4
DHTD-30 | Analysis & Design | Elaboration | design a simple tower drawable |  | 4 | 3.5 | Luca | 3.5
DHTD-31 | Lecture Requirements | Elaboration | Blog Entry Week 8 |  | 1 | 2 | Nicolas | 2
DHTD-32 | Lecture Requirements | Elaboration | Write comments to other groups (Week 8) |  | 1 | 1 | Nicolas | 1
DHTD-35 | Implementation | Construction | Calculate the exact angle and align the tower to enemies |  | 4 | 3.5 | Luca | 3
[7 empty] | Nicolas | 0.5
DHTD-36 | Analysis & Design | Elaboration | Create the background-map for the game-page |  | 2 | 2 | Luca | 2
DHTD-39 | Analysis & Design | Construction | Create Path-Designs and implement into the game |  | 8 | 8 | Luca | 8
DHTD-40 | Testing | Elaboration | Feature Files and automatic testing with Cucumber | start the game from the menu | 8 | 11 | Fabian | 2.5
[7 empty] | Nicolas | 8.5
DHTD-41 | Testing | Construction | Unit Test for tower rotation |  | 5 | 3.75 | Luca | 3.25
[7 empty] | Fabian | 0.25
[7 empty] | Nicolas | 0.25
DHTD-42 | Lecture Requirements | Elaboration | Blog Entry Week 9 |  | 3 | 4 | Fabian | 1
[7 empty] | Luca | 2
[7 empty] | Nicolas | 1
DHTD-43 | Lecture Requirements | Elaboration | Write comments to other groups (Week 9) |  | 1 | 1 | Luca | 1
DHTD-44 | Analysis & Design | Elaboration | Create MVC model |  | 3 | 2 | Fabian | 0.75
[7 empty] | Luca | 0.5
[7 empty] | Nicolas | 0.75
DHTD-38 | Implementation | Construction | GE: Build towers when a button is clicked | build towers on selected area | 2 | 2.5 | Fabian | 2
[7 empty] | Nicolas | 0.25
[7 empty] | Luca | 0.25
DHTD-49 | Implementation | Construction | GE: remove Tower on click | build towers on selected area | 2 | 2 | Fabian | 1.5
[7 empty] | Nicolas | 0.25
[7 empty] | Luca | 0.25
DHTD-50 | Implementation | Construction | GE: spawn wave button | start waves | 2 | 2 | Fabian | 1.5
[7 empty] | Nicolas | 0.25
[7 empty] | Luca | 0.25
DHTD-46 | Analysis & Design | Inception | Create UCS for UC "build towers on selected area" | build towers on selected area | 3 | 2 | Nicolas | 1.75
[7 empty] | Luca | 0.25
DHTD-47 | Analysis & Design | Inception | Create UCS for UC "Return to main menu" | return to main menu | 2 | 1.5 | Nicolas | 1.25
[7 empty] | Luca | 0.25
DHTD-54 | Lecture Requirements | Elaboration | create handout for midterm presentation |  | 4 | 3.5 | Nicolas | 3.25
[7 empty] | Luca | 0.25
DHTD-53 | Lecture Requirements | Elaboration | create the presentation for midterm exam |  | 15 | 12.25 | Nicolas | 5.5
[7 empty] | Luca | 4.5
[7 empty] | Fabian | 4.25
DHTD-51 | Lecture Requirements | Elaboration | Blog Entry Week 10 |  | 6 | 3.5 | Nicolas | 3.5
DHTD-52 | Lecture Requirements | Elaboration | Write Comments to other groups (Week 10) |  | 1 | 1 | Luca | 1

## Use Case Overview
UC | UC description | Documentation (h) | Coding (h) | Testing (h) | Warm-Up time (h) | Total (h) | FP
1 | start the game from the menu* | 5 | 27 | 8 | 5 | 40 | ?
2 | start waves | 5 | 2 | 0.5 | 0 | 7.5 | ?
3 | build towers on selected area | 2 | 4.5 | 0 | 0 | 6.5 | ?
4 | return to main menu | 1.5 | 0 | 0 | 0 | 1.5 | ?
*start the game from the menu:
This Use Case includes the implementation of the gameengine in order to have a base for playing the game